## Pro. Plan (2025-26)
Annual Procurement Plan OF PMDC For The Year 2025-2026 (CAPEX)
(Under rule 8 and 9 of the Public Procurement Rule 2004)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Sr. No. | Name of Procurement (Description) | Estimated Cost Rs. in million | Procurement Method | Tentative date of Procurement Notice Publication | Tentative date of Award of Contract | Tentative date of Completion | Remarks
1-PMDC SBU SALT, KHEWRA
MINES DEVELOPMENT/ REHABILITION:
1 | Retaining Wall of Western Hill Road | 2 | Open Competitive Bidding | 2025-12-01 | 2026-01-14 | 2026-05-14
PLANT & MACHINERY
1 | 4 Core 35 mm Aluminium Cable (3000 meters) | 5 | Open Competitive Bidding | 2026-01-01 | 2026-02-15 | 2026-04-16
2 | HT Poles & Transformer (150 KVA) | 6 | Open Competitive Bidding | 2026-02-10 | 2026-03-27 | 2026-06-25
3 | Solar System for Main Office (20 KVA) | 3 | Open Competitive Bidding | 2026-02-15 | 2026-04-01 | 2026-06-15
4 | Ventilation fan and flexible ventilation duct line for Main Mine and Khura Mine | 7 | Open Competitive Bidding | 2026-01-20 | 2026-03-06 | 2026-06-04
5 | New Telephone Exchange/Wireless intercom | 2 | Open Competitive Bidding | 2026-01-31 | 2026-03-31 | 2026-06-30 | Consolidated Tender
6 | Main Switches, DOL Starter Panels and Safety Mats | 1.2 | Open Competitive Bidding | 2026-02-01 | 2026-03-18 | 2026-06-16
7 | Roof Scaling Machine | 50 | Open Competitive Bidding | 2025-12-10 | 2026-01-24 | 2026-06-30 | Depends on lead time
8 | Dust Collector for Grinding Plants | 1.5 | Open Competitive Bidding | 2025-12-15 | 2026-01-29 | 2026-03-30
Computer & Sundary Equipment
1 | Laptops/Desktops/Scanner | 3.4 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-03-31 | Consolidated Tender
2 | Arm & Ammunitions | 1.5 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-05-28 | Consolidated Tender
3 | CCTV Cameras for Misc locations (Main office, guest house, voucher office) | 4.5 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-05-15
4 | Misc.Equipments (Batteries, Ticketing Station for Car parking etc, Supporting Structure)) | 4.2 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-05-28 | More than one tender
CIVIL WORKS
1 | Construction,Renovation & Major Repairs (Misc Jobs) | 51.5 | Open Competitive Bidding | 2026-01-15 | 2026-03-01 | 2026-06-30 | Partially completion expected. More than one tender required
2 | Installation of Pre Fabricated Roof of Power house | 5 | Open Competitive Bidding | 2026-02-10 | 2026-03-27 | 2026-06-30
3 | Underground Road Fencing of Main Mine | 4 | Open Competitive Bidding | 2026-02-01 | 2026-03-18 | 2026-06-30
TRANSPORT
1 | Toyota Hilux Revo G double cabin 4x4 (2 Nos.) | 30 | Direct Contracting | 2025-12-02 | 2025-12-31 | 2026-03-31
FURNITURE, FIXTURE & EQUIPMENT
1 | Furniture, fixtures and equipment for the Main Office/Guest house | 6.8 | Open Competitive Bidding | 2026-04-01 | 2026-05-26 | 2026-07-25 | More than one tender required
HSE
1 | Multi Gas Detector | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitors (02 Nos.) | 0.37 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
4 | Strechers and Spinal Boards (06 Nos.) | 0.14 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
5 | Noise Level Meters | 0.05 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
6 | PPE Storage Lockers (02 Nos.) | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
7 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
8 | Under Ground Waste Collection System (04 Nos.) | 0.075 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
9 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
HSE Five Years Plan
1 | Safety Equipment Modernization | 1 | Open Competitive Bidding | 2026-01-08 | 2026-03-01 | 2026-06-15
2 | Emergency Response Equipment | 0.8 | Open Competitive Bidding | 2026-02-10 | 2026-03-15 | 2026-06-30
| Head Total | 194.685
2-PMDC SBU SALT, Warcha
MINES DEVELOPMENT/ REHABILITION:
1 | Design Study for New Mine Development | 30 | Open Competitive Bidding | 2025-12-15 | 2026-01-14 | 2026-10-11 | Partial completion expected
2 | New Ventilation Tunnels Main Mine | 30 | Open Competitive Bidding | 2026-01-20 | 2026-03-06 | 2026-07-04 | Partially completion expected
PLANT & MACHINERY
1 | Pay Loader 3-4 MT Bucket Capicity | 35 | Open Competitive Bidding | 2025-12-01 | 2026-01-15 | 2026-06-14 | Depends on quoted lead time
2 | Overhauling of Cat 950 GC hydraulic system along with associated spare parts | 10 | Direct Contracting | 2026-02-01 | 2026-02-28 | 2026-06-30
3 | Trolly & Bucket for Tractor | 4 | Open Competitive Bidding/APM | 2026-01-01 | 2026-02-15 | 2026-05-16
4 | GI Pipe/Polyethene pipe/Canvas Hose Pipe | 8 | Open Competitive Bidding | 2026-02-01 | 2026-02-28 | 2026-06-30
5 | Electrification of Main Mine for water pumping (PVC cable 4core 25mm) | 8 | Open Competitive Bidding | 2026-02-05 | 2026-03-22 | 2026-06-20
6 | New Telephone Exchange/Wireless intercom | 2 | Open Competitive Bidding | 2026-01-31 | 2026-03-31 | 2026-06-30
7 | Solar based Street/Flood, lights along with poles and accessories | 5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-06-30
8 | Misc. Equipments for Grinding Plants (Color sorting, Cutter,Disc Mill) | 15.5 | Open Competitive Bidding | 2026-01-10 | 2026-02-28 | 2026-06-30
9 | New Grinding Plant | 100 | Open Competitive Bidding | 2025-12-15 | 2026-02-01 | 2026-06-30 | Partial completion expected
10 | Roof Scalining Machine | 50 | Open Competitive Bidding | 2025-12-15 | 2026-02-01 | 2026-06-30 | As per quoted lead time
11 | Electrification scheme, Cable and Electrical items for Jumbo drill | 12 | Open Competitive Bidding | 2025-12-20 | 2026-02-03 | 2026-03-05
Computer & Sundary Equipment
1 | Laptop/Desktop/Printers | 2.7 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31 | Consolidated Tender
2 | Arm & Ammunitions | 2.825 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-05-28 | Consolidated Tender
3 | CCTV Cameras for different project locations | 3 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-05-15
4 | Misc.Equipments (Telescopic Compass with tripod 01 No) | 0.25 | Alternative Procurement Method | 2026-01-02 | 2026-01-17 | 2026-02-01
CIVIL WORKS
1 | Construction,Renovation & Major Repairs of Misc Civil Projects/Jobs | 104.3 | Open Competitive Bidding | 2025-12-15 | 2026-01-31 | 2026-06-30 | More than one tender might required. Partially completion expected
2 | Construction of Water Tank & Water Bore | 3.5 | Open Competitive Bidding | 2026-03-01 | 2026-04-30 | 2026-05-31
TRANSPORT
1 | Toyota Hilux Revo G 4X4 (2 Num) + Loader Rikhsha (2 Num) | 30.9 | Direct Contracting | 2025-12-02 | 2025-12-31 | 2026-03-31
FURNITURE, FIXTURE & EQUIPMENT
1 | Furniture, fixtures and equipment for the Main office/site offices | 7.16 | Open Competitive Bidding | 2026-02-10 | 2026-03-31 | 2026-05-31 | More than one tender might required
HSE
1 | Multi Gas Detector | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitor | 0.37 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
4 | Strechers and Spinal Boards | 0.14 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
5 | Noise Level Meters | 0.05 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
6 | PPE Storage Lockers | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
7 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
8 | Under Ground Waste Collection System | 0.075 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
9 | Water Filtration Plant | 1.5 | Open Competitive Bidding | 2026-01-01 | 2026-03-15 | 2026-05-31
10 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
HSE Five Years Plan
1 | Safety Equipment Modernization | 1 | Open Competitive Bidding | 2026-01-08 | 2026-03-01 | 2026-06-15 | Consolidated Tender
2 | Emergency Response Equipment | 0.8 | Open Competitive Bidding | 2026-02-10 | 2026-03-15 | 2026-06-30 | Consolidated Tender
| Head Total | 471.72
3-PMDC SBU SALT, Makrach
MINES DEVELOPMENT/ REHABILITION:
1 | Design Study for New Mine Development | 30 | Open Competitive Bidding | 2025-12-15 | 2026-01-14 | 2026-10-11 | Partial completion expected
2 | New Ventilation Tunnels | 6.5 | Open Competitive Bidding | 2026-03-01 | 2026-04-30 | 2026-06-30
PLANT & MACHINERY
1 | Water pumping System | 0.7 | Open Competitive Bidding/APM | 2026-03-15 | 2026-05-31 | 2026-06-30
2 | Ventilation fan and flexible ventilation duct line | 1.5 | Open Competitive Bidding/APM | 2026-03-15 | 2026-05-31 | 2026-06-30
3 | China Chakki, along with the power supply | 5 | Open Competitive Bidding/APM | 2025-12-26 | 2026-02-28 | 2026-04-30
CIVIL WORKS
1 | Construction,Renovation & Major Repairs (Misc Jobs) | 12.5 | Open Competitive Bidding | 2026-01-10 | 2026-02-25 | 2026-06-30 | More than one tender might required
FURNITURE, FIXTURE & EQUIPMENT
1 | Air Conditioner (1 No.)-for sale branch | 0.2 | Alternative Procurement Method | 2025-12-10 | 2025-12-31 | 2026-01-15
2 | Computers & Printer | 0.9 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-03-31 | Consolidated Tender
HSE
1 | Multi Gas Detector | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitor | 0.37 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
4 | Strechers and Spinal Boards | 0.12 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
5 | Noise Level Meters | 0.05 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
6 | PPE Storage Lockers | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
7 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
8 | Under Ground Waste Collection System | 0.075 | Alternative Procurement Method | 2025-11-01 | 2025-12-15 | 2026-02-28
9 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
10 | Medical Dispensery | 2 | Open Competitive Bidding | 2026-01-01 | 2026-03-01 | 2026-06-30
HSE Five Years Plan
1 | Safety Equipment Modernization | 0.5 | Open Competitive Bidding | 2026-01-08 | 2026-03-01 | 2026-06-15 | Consolidated Tender
2 | Emergency Response Equipment | 0.4 | Open Competitive Bidding | 2026-02-10 | 2026-03-15 | 2026-06-30 | Consolidated Tender
| Head Total | 64.465
4-PMDC SBU SALT, Kalabagh
MINES DEVELOPMENT/ REHABILITION:
1 | Design Study for New Mine Development | 30 | Open Competitive Bidding | 2025-12-15 | 2026-01-14 | 2026-10-11 | Partial completion expected
PLANT & MACHINERY
1 | Transformer (500 KVA) for D-14 with poles and conductors | 6 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-05-28
CIVIL WORKS
1 | Construction,Renovation & Major Repairs (Misc Jobs) | 18 | Open Competitive Bidding | 2025-12-20 | 2026-02-20 | 2026-06-30 | More than one tender
Sundary Equipment
1 | Arm & Ammunitions | 0.5 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-05-28 | Consolidated Tender
2 | Total Station (for precise survey to ease the mines development/advancement) | 3.5 | Open Competitive Bidding | 2025-12-15 | 2026-01-29 | 2026-04-29
3 | CCTV Cameras with accessories at 4 weighbridges & thermal printers for Weighbridges | 0.5 | Alternative Procurement Method | 2025-11-30 | 2025-12-15 | 2026-02-28
FURNITURE, FIXTURE & EQUIPMENT
1 | Furniture for Main office and Time office | 0.5 | Alternative Procurement Method | 2025-12-20 | 2026-02-15 | 2026-03-30
2 | Computers/Laptops(7 Num) & Printer | 1.8 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31 | Consolidated Tender
| Refrigerator & Ovan for Guest House | 0.45 | Alternative Procurement Method | 2025-11-30 | 2025-12-15 | 2026-02-28
HSE
1 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Strechers and Spinal Boards | 0.12 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
3 | Water Filtration Plant | 1.5 | Open Competitive Bidding | 2026-01-01 | 2026-03-15 | 2026-05-31
4 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
HSE Five Years Plan
1 | Safety Equipment Modernization | 0.8 | Open Competitive Bidding | 2026-01-08 | 2026-03-01 | 2026-06-15 | Consolidated Tender
2 | Emergency Response Equipment | 0.5 | Open Competitive Bidding | 2026-02-10 | 2026-03-15 | 2026-06-30 | Consolidated Tender
| Head Total | 65.87
5-PMDC SBU SALT, JBK
PLANT & MACHINERY
1 | Solar System for Main Office (15 KVA) | 3 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-05-30
CIVIL WORKS
1 | Boundary wall raising/major repair (B- Khel colony) | 2.5 | Open Competitive Bidding | 2026-02-15 | 2026-04-15 | 2026-06-30
FURNITURE, FIXTURE & EQUIPMENT
1 | Furniture, fixtures(4 Ac) and equipment for the Main office/site offices | 1.8 | Open Competitive Bidding/APM | 2026-01-31 | 2026-03-15 | 2026-05-15
2 | Professional Printer & Scanner for ERP Integration | 0.4 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-03-31 | Consolidated tender
Transport
1 | Transport (Bikes 2 Num) | 0.7 | Alternative Procurement Method | 2025-12-15 | 2025-12-30 | 2026-01-14
HSE
1 | Multi Gas Detector | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitor | 0.37 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
4 | Strechers and Spinal Boards | 0.12 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
5 | Noise Level Meters | 0.05 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
6 | PPE Storage Lockers | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
7 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
8 | Under Ground Waste Collection System | 0.075 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
9 | Water Filtration Plant | 1.5 | Open Competitive Bidding | 2026-01-01 | 2026-03-15 | 2026-05-31
10 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
Five Years Plan
1 | Safety Equipment Modernization | 0.4 | Open Competitive Bidding/APM | 2026-01-08 | 2026-03-01 | 2026-06-15
2 | Emergency Response Equipment | 0.3 | Open Competitive Bidding/APM | 2026-02-10 | 2026-03-15 | 2026-06-30
| Head Total | 14.865
6- PMDC SBU COAL SOR-RANGE
PLANT & MACHINERY
1 | Extension of Track Dips Line (1000 ft FY 2025-26) | 3.75 | Open Competitive Bidding | 2025-12-01 | 2026-01-15 | 2026-06-14
2 | C.T Operated Three Phase Energy Meters (500-A), with D.B'S & Stand (04-Nons Each) | 1.5 | Open Competitive Bidding | 2025-12-02 | 2026-01-16 | 2026-06-15
3 | Relays, Opening & Closing Closure for 11-KV H.T Panels at Power House (05 Nos Each) | 4 | Open Competitive Bidding | 2025-12-05 | 2026-02-15 | 2026-06-15
4 | Power Breakers (500 Amp),Capacitors (80-KVAR)(02 Nons Each) | 0.6 | Open Competitive Bidding | 2025-12-08 | 2026-02-15 | 2026-06-15
5 | C.T(Current Transformer) 03 Nons P.T(Potential Transformer) 03 Nons & H.T Kits 6 Nons for Wapda Trollies | 1 | Open Competitive Bidding | 2025-12-20 | 2026-02-15 | 2026-06-15
6 | 15-HP Submersible Pumps (02 Nons), Flame Proof Panels with Dol Starters (02 Nons),4-Core 25-MM2 Armored Cable 1000-Meters | 2 | Open Competitive Bidding | 2025-12-15 | 2026-01-29 | 2026-05-29
7 | Major Repair of LOCO Motives | 2.2 | Open Competitive Bidding/APM | 2026-01-10 | 2026-02-28 | 2026-06-15
8 | Control Room Infrastructure (Camera and associated installation) | 5 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-06-15
9 | Under Ground & Surface Communication System | 5 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-06-15
10 | Exploder Machines | 1.5 | Open Competitive Bidding | 2025-12-10 | 2026-01-24 | 2026-03-25
11 | Energy Meter Installation | 3.5 | Open Competitive Bidding | 2026-02-01 | 2026-03-18 | 2026-06-16
CIVIL WORK
1 | Construction & Renovation of Dispensory | 2 | Open Competitive Bidding | 2026-01-15 | 2026-03-01 | 2026-06-29
2 | Installation of Shed Car Parking for Officers/Vistor | 0.5 | Alternative Procurement Method | 2026-01-10 | 2026-01-25 | 2026-03-26
3 | Mine Mouth Arching | 1 | Open Competitive Bidding | 2026-01-15 | 2026-03-01 | 2026-06-29
Sundary Equipment
1 | Fuel Dispenser Pump | 0.5 | Alternative Procurement Method | 2026-01-08 | 2026-01-23 | 2026-02-22
2 | Photostate Machine | 0.5 | Alternative Procurement Method | 2026-01-05 | 2026-01-20 | 2026-02-19
3 | Professional Printer & Scanner for ERP Integration | 0.4 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31
Furniture and Fixtures
1 | Furniture & Fixture | 0.35 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-04-02
HSE
1 | Multi Gas Detector | 1 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitor | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | Breathing Apparatus & Self Rescuer | 5 | Open Competitive Bidding | 2026-01-31 | 2026-03-15 | 2026-04-30
4 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
5 | Strechers and Spinal Boards | 0.12 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
6 | Noise Level Meters | 0.05 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
7 | PPE Storage Lockers | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
8 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-02-01 | 2026-02-28 | 2026-03-30
9 | Under Ground Waste Collection System | 0.075 | Alternative Procurement Method | 2026-01-15 | 2026-02-28 | 2026-04-30
10 | Water Filtration Plant | 1.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
11 | Construction of HSE room & First aid room | 2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
12 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
13 | Hand Held infra red thermal camera flame proof | 1.5 | Open Competitive Bidding | 2026-02-01 | 2026-02-28 | 2026-03-30
Five Years Plan
1 | Safety Equipment Modernization | 1 | Open Competitive Bidding | 2026-02-01 | 2026-03-18 | 2026-05-17
2 | Monitoring Systems Installation | 4 | Open Competitive Bidding | 2026-02-01 | 2026-03-18 | 2026-05-17
3 | Emergency Response Equipment | 1 | Open Competitive Bidding | 2026-02-01 | 2026-03-18 | 2026-05-17
| Head Total | 56.195
7- PMDC SBU COAL- SHARIGH
PLANT & MACHINERY
1 | Solar Power System & Street Lights (10 KVA) | 3.4 | Open Competitive Bidding | 2026-01-01 | 2026-02-15 | 2026-05-16
2 | Under Ground & Surface Communication System | 5 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-06-15
CIVIL WORKS
1 | Construction & Renovation (Construction of Rooms + Renovation of Guest house) | 5 | Open Competitive Bidding | 2026-01-01 | 2026-02-15 | 2026-05-16
2 | Installation of Shed Car parking for officers/vistor | 0.5 | Alternative Procurement Method | 2025-12-30 | 2026-01-14 | 2026-02-28
Transport
1 | Honda Motorcycle 125cc | 0.35 | Alternative Procurement Method | 2025-12-25 | 2026-01-09 | 2026-02-23
2 | Major Repair of Suzuki Pothohar (QAF 2248) | 1 | Alternative Procurement Method | 2026-03-10 | 2026-03-25 | 2026-05-24
Computer
1 | Laptop (with printer) | 0.3 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31
2 | Professional Printer & Scanner for ERP Integration | 0.4 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31
FURNITURE & FIXTURE
1 | Furniture & Fixture (Misc items) | 1.7 | Open Competitive Bidding/APM | 2026-02-01 | 2026-03-15 | 2026-06-30 | As per need basis. More than one case
Sundry Equipment
1 | Walkie-Talkie for Communication | 0.45 | Alternative Procurement Method | 2026-01-01 | 2026-01-16 | 2026-01-31
HSE
1 | Multi Gas Detector | 1 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitor | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | Breathing Apparatus & Self Rescuer | 4 | Open Competitive Bidding | 2026-01-31 | 2026-03-15 | 2026-04-30
4 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
5 | Strechers and Spinal Boards | 0.12 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
6 | Noise Level Meters | 0.05 | Open Competitive Bidding | 2026-02-01 | 2026-02-28 | 2026-03-30
7 | PPE Storage Lockers | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
8 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-02-01 | 2026-02-28 | 2026-03-30
9 | Under Ground Waste Collection System | 0.075 | Alternative Procurement Method | 2025-11-24 | 2026-01-26 | Mar-26
10 | Water Filtration Plant | 1.5 | Open Competitive Bidding | 2025-11-24 | 2026-01-26 | Mar-26
11 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
12 | Smoke tube for stopping Leakage/ Smoke detector | 0.3 | Alternative Procurement Method | 2025-12-15 | 2026-01-15 | 2025-02-15
Five Years Plan
1 | Safety Equipment Modernization | 0.8 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-06-15
2 | Monitoring Systems Installation | 3 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-06-15
3 | Emergency Response Equipment | 0.8 | Open Competitive Bidding | 2026-02-10 | 2026-03-15 | 2026-06-30
| Head Total | 33.395
8- PMDC SBU COAL- Degari
PLANT & MACHINERY
1 | Solar Power System (3 KVA) | 0.5 | Alternative Procurement Method | 2026-01-25 | 2026-02-09 | 2026-03-26
CIVIL WORKS
1 | Water tank | 0.05 | Alternative Procurement Method | 2025-12-01 | 2025-12-15 | 2025-12-31
COMPUTERS
1 | Laptop (with printer) | 0.3 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31 | Consolidated tender
2 | Professional Printer & Scanner for ERP Integration | 0.4 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31 | Consolidated tender
HSE
1 | Multi Gas Detector | 1 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
2 | Air Quality Monitor | 0.55 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
3 | Breathing Apparatus & Self Rescuer | 4 | Open Competitive Bidding | 2026-01-31 | 2026-03-15 | 2026-04-30
4 | First Aid Stations | 1.2 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
5 | Strechers and Spinal Boards | 0.12 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-04-30
6 | Noise Level Meters | 0.05 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
7 | PPE Storage Lockers | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-28 | 2026-03-30
8 | Washing & Sterilization Station | 1.2 | Open Competitive Bidding | 2026-02-01 | 2026-02-28 | 2026-03-30
9 | Under Ground Waste Collection System | 0.0748 | Alternative Procurement Method | 2025-11-24 | 2026-01-26 | Mar-26
10 | Lux meter/ Hygrometer/ PHmeter/TDS Meter | 0.5 | Open Competitive Bidding | 2026-01-15 | 2026-02-28 | 2026-04-30
11 | Smoke tube for stopping Leakage/ Smoke detector | 0.3 | Alternative Procurement Method | 2025-12-15 | 2026-01-15 | 2025-02-15
Five Years Plan
1 | Safety Equipment Modernization | 0.5 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-06-15
2 | Monitoring Systems Installation | 2.5 | Open Competitive Bidding | 2026-02-01 | 2026-03-15 | 2026-06-15
3 | Emergency Response Equipment | 0.4 | Open Competitive Bidding | 2026-02-10 | 2026-03-15 | 2026-06-30
| Head Total | 13.8448
9-PMDC SBU TOURIST RESORT KHEWRA
PLANT & MACHINERY
1 | Vertical Suction Pumps (Qty 2 Nos.) | 2 | Open Competitive Bidding | 2026-02-05 | 2026-03-22 | 2026-05-21
2 | Heavy Densit Polyethelene pipe | 1 | Open Competitive Bidding | 2026-02-05 | 2026-03-22 | 2026-05-21
Civil Works
1 | Construction of new Souvenir Shop at Resort | 3 | Open Competitive Bidding | 2026-01-08 | 2026-02-22 | 2026-04-23
2 | Extension of Fiber shed in Main Sitting Area and Parking Area | 5 | Open Competitive Bidding | 2026-02-25 | 2026-04-11 | 2026-06-10
3 | Complete Ceramic Tile Works on Front Wall of reception hall building With PMDC Monogram | 1.2 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-06-14
4 | Civil works of guest house(Precast roof, Paneling and wooden floor) | 4 | Open Competitive Bidding | 2026-03-01 | 2026-04-15 | 2026-06-14
5 | Complete Renovation with Wood Works of Different Chambers of Visiting Area | 2 | Open Competitive Bidding/APM | 2026-02-01 | 2026-03-18 | 2026-05-17 | As per requirement, more than one tender required
6 | Major Repair of Sheesh Mahal Bridge | 3 | Open Competitive Bidding | 2026-03-15 | 2026-04-29 | 2026-06-28
7 | Repair of Pony Track and Construction of Hill Top Refreshment point along telescopes for views | 2.5 | Open Competitive Bidding | 2025-12-10 | 2026-01-24 | 2026-04-24
8 | Construction of New Drain from Main Visiting Tunnel (LLT) and Sheesh Mahal (4000) ft | 3 | Open Competitive Bidding | 2026-03-20 | 2026-05-04 | 2026-08-02
9 | Construction of Time Office and Washrooms at New Entry Tunnel | 2 | Open Competitive Bidding | 2026-03-05 | 2026-04-19 | 2026-07-03
10 | Construction of Fountain with Sculpture of Alexander the Great on Horse in Fiber Glass | 2 | Open Competitive Bidding | 2026-01-31 | 2026-03-17 | 2026-05-16
11 | Replacement of Old Wooden Sleepers and Planks, etc | 2 | Open Competitive Bidding/APM | 2026-03-31 | 2026-05-15 | 2026-08-13 | As per requirement, more than one tender required
12 | Monuments of Shah Faisal Masjid and Bab-e-Khyber | 1.5 | Open Competitive Bidding/APM | 2026-02-01 | 2026-03-18 | 2026-06-16 | Tiles inhouse procurement
13 | Construction of Salt Bedroom | 3 | Open Competitive Bidding/APM | 2026-02-01 | 2026-03-18 | 2026-06-16 | Inhouse arrangement
TRANSPORT
1 | Loader Ricksaw (1 No.) | 0.5 | Alternative Procurement Method | 2025-12-10 | 2025-12-25 | 2026-01-24
2 | LOCO Engine Tyers 4 Nos with spare parts | 1.5 | Open Competitive Bidding | 2025-12-10 | 2026-01-24 | 2026-04-24
Computer
1 | Computer set with printers (2 Nos) | 0.5 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31
FURNITURE, FIXTURE & EQUIPMENT
1 | Ceiling Fans | 0.2 | Alternative Procurement Method | 2026-01-01 | 2026-01-16 | 2026-02-15
2 | Steel Almirahs (3 No,s) | 0.15 | Alternative Procurement Method | 2026-01-10 | 2026-01-25 | 2026-02-24
3 | Sofa sets for guest house (3 Sets) | 0.5 | Alternative Procurement Method | 2026-01-15 | 2026-01-30 | 2026-03-01
4 | Office Tables and Chairs, Computer table and Chairs | 0.15 | Alternative Procurement Method | 2026-01-15 | 2026-01-30 | 2026-03-01
5 | Fiber Chairs and Tables for Visitors | 2 | Open Competitive Bidding | 2026-03-31 | 2026-05-15 | 2026-06-29
| Head Total | 42.7
10- BD, HEAD OFFICE ISLAMABAD & Regional Offices
BUSINESS DEVELOPMENT BUDGET
1 | Antimony Exploration Project (Phase III & IV) | 120 | Open Competitive Bidding | 2026-04-01 | 2026-05-16 | 2026-10-13
2 | CSR During Exploration of Antimony Blocks | 15 | As per management decision. PPRA rules will be followed if any procurement is made
3 | Gilgit Baltistan 9 Explorations Prospects – (Licensing Rights and Phase – I (RS) explorations) | 20 | Subject to lease finalization
4 | Workstations for Exploration Department | 6.5 | Open Competitive Bidding | 2025-09-15 | 2025-11-14 | 2026-01-13
5 | Acquisition & exploration of Chromite Mining Lease in Malakand | 20 | Not applicable
6 | Feasibility study of Coal to Coke and Humic Acid Plant | 15 | Open Competitive Bidding/APM | 2026-01-15 | 2026-03-01 | 2026-05-30
7 | EL acquisition rights of Iron Ore, Base & Precious metal, Metalliferous resources of placer gold & REE's block | 25 | Not applicable
CIVIL CONSTRUCTION
1 | Construction of New Office Building ( Area ~18002 sqft) | 181.82 | Open Competitive Bidding | 2025-12-15 | 2026-02-13 | 2026-10-21 | 50% completion expected
2 | Construction/Renovation Misc Works at Queeta Office | 35.1 | Open Competitive Bidding | 2025-12-01 | 2026-01-31 | 2026-06-30 | More than one tender required
TRANSPORT
1 | Toyota Fortuner GR-S 2770cc | 25 | Direct Contracting | 2025-11-20 | 2025-12-05 | 2026-03-05
2 | Car 1300 cc (Toyota Yaris 1.3 GLI Auto)- (02) | 10.16 | Direct Contracting | 2025-11-20 | 2025-12-05 | 2026-03-05
3 | Cars 1200 cc - (Suzuki Swift) (3 Nos.) | 14.7 | Direct Contracting | 2025-11-20 | 2025-12-05 | 2026-03-05
4 | MPV 1200cc- (Changan Karvaan) (2Nos.) | 6.5 | Direct Contracting | 2025-11-20 | 2025-12-05 | 2026-03-05
5 | Major Repair of Vehicles transffered from Lakhra (Queeta Office) | 3 | Open Competitive Bidding/APM | 2025-12-01 | 2026-01-15 | 2026-03-16 | More than one tender required
Office Equipment & Fixtures
1 | Replacement of Old Furniture/Fixtures (HO) | 3 | Alternative Procurement Method | On Need Basis
2 | Furniture for Conference Room and Guest House (Queta) | 2.03 | Open Cometitive Bidding | 2026-02-01 | 2026-03-20 | 2026-03-30
3 | Board Room Conference Wooden table, 20 wooden chairs, Guest room furniture(Peshawar) | 1.3 | Open Cometitive Bidding | 2026-02-01 | 2026-03-18 | 2026-05-17
4 | Multimedia and LED(s) for Conference Room and Guest House (Queta) | 1.2 | Open Competitive Bidding | 2026-03-01 | 2026-03-20 | 2026-03-31
5 | LED TV 68" Board Room 55" Guest Room (Peshawar) | 0.4 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-03
6 | Air Conditioners (15 Num) HO | 3 | Open Competitive Bidding/APM | On Need Basis
7 | Invertor AC (2 for Conference hall & 2 for New Guest House) (One for Off.Inc one for existing Guest House) (Queta) | 1.2 | Open Competitive Bidding/APM | 2026-03-01 | 2026-03-16 | 2026-03-31
8 | Air Conditioners (Two num) Peshawar | 0.4 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-03
9 | Air Conditioners (Multan) | 0.2 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-03
10 | Solar System 10KVA for Office (Queta) | 2 | Open Competitive Bidding | 2026-01-01 | 2026-02-15 | 2026-05-16
11 | Misc. Electrical/Office Items (fans, refrigerator, water dispenser,bracket fans,grass cutting machine, coffee machine)-HO | 2.18 | Open Competitive Bidding/APM | 2026-01-01 | 2026-02-15 | 2026-05-16 | More than one tender required
12 | Misc Electrical Items (Photostate machine, water dispenser,intercom, UPS)-Queta | 0.79 | Open Competitive Bidding/APM | 2026-02-01 | 2026-02-16 | 2026-03-03 | More than one tender required
13 | Misc. Electrical Items (Ceiling fans 6 ) Peshawar | 0.06 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-03
14 | Misc. Electrical Items (Ceiling fans 2)-Multan | 0.02 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-03
Computers
1 | Laptop (33)/Printer/UPS (Head office) | 11.7 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31
2 | Laptops with Printer (Queeta) | 0.6 | Open Competitive Bidding | 2025-11-10 | 2025-12-20 | 2026-01-31
3 | Laptop/Printer/UPS (Multan) | 0.34 | Open Competitive Bidding/APM | 2025-11-10 | 2025-12-20 | 2026-01-31
Sundary Equipment
1 | CCTV/UPS/Batteries (HO) | 5.65 | Open Competitive Bidding | 2026-01-01 | 2026-02-15 | 2026-03-17 | More than one tender required
2 | CCTV Cameras (Peshawar) | 0.25 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-18
3 | CCTV Cameras (Queeta) | 0.25 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-18
4 | CCTV Cameras (Multan) | 0.1 | Alternative Procurement Method | 2026-02-01 | 2026-02-16 | 2026-03-18
5 | Centralized Internet Facility with Equipment. (HO) | 2.5 | Open Competitive Bidding | 2025-12-01 | 2026-01-15 | 2026-03-16
6 | Geological field survey equipment | 15 | Open Competitive Bidding | 2025-12-10 | 2026-01-24 | 2026-03-25
7 | Arms & Ammunition (HO) | 0.5 | Open Competitive Bidding | 2026-03-01 | 2026-03-16 | 2026-04-15
| Head Total | 552.45
| SBU | PK (Million) | Number of Projects
| Salt | 811.605 | 112
| Coal | 103.4348 | 78
| Tourist Resort (TR) | 42.7 | 23
| Head/Brach Offices & BD | 552.45 | 37
| Total Capex Projects | 1510.1898 | 250
1 | Consolidated tenders(where possible) will be issued for similar items required at different sites (IT,HSE, Solar etc.)
2 | EPADS(PPRA online portal) will be used for transparent tendering and to enhance the suppliers base
Formulas:
Tentative date of Completion = [Tentative date of Award of Contract]+120
Tentative date of Completion = +[Tentative date of Award of Contract]+60

## Sheet1 (hidden)
Procurement Strategy to Optimize Cost and Enhance Efficiency
Sr# | Plan | Target Dates
1 | Establish Strategic Framework Agreements for Recurring Procurement Needs (Laptops, AC, Misc IT Equipment etc.) | 2025-09-01
2 | Optimize Procurement Efficiency through Category Consolidation and Lotting | On goiong
3 | Ensure Full Utilization of the PPRA EPADS Portal for Transparent Tendering | 2025-07-25
4 | Leverage ERP Systems to Automate Procurement Workflows | 2025-07-25
5 | Development of Procurement Policy Manual along well-structured procurement team | 2025-12-31